## Sheet1
Project Name: ABC House |  |  |  | Address: ABC House, City Road, London W1
Job No: 1234 |  |  |  | Date: 10th June 2013
|  | Order By | Lead In Period (Weeks) | Expected Delivery to Site | Status/Comments
Reception Desk | P | -42 | 6 |  | Allow for an additional 3 weeks for drawings and approvals.
F
A
Library Unit | P | -42 | 6 |  | Allow for an additional 3 weeks for drawings and approvals.
F
A
Lights | P | -35 | 5
F
A
Carpet and Floor finishes | P | -42 | 6
F
A
Airedale Comms Units | P | -42 | 6 |  | Allow for an additional 2 weeks for drawings and approvals.
F
A
Storage Unit | P | -42 | 6 |  | Allow for an additional 3 weeks for drawings and approvals.
F
A
Ceramic floor tiles | P | -28 | 4
F
A
Trox linear grilles | P | -28 | 4
F
A
Distribution boards / panels | P | -42 | 6
F
A
Down lighters | P | -56 | 8
F
A
FCU | P | -56 | 8
F
A
FCU controllers | P | -28 | 4
F
A
Fire alarm panel | P | -42 | 6
F
A
Gas suppression bottles | P | -56 | 8
F
A
Gas suppression panel | P | -42 | 6
F
A
General LV switchgear | P | -42 | 6
F
A
Grilles and plenums | P | -28 | 4
F
A
HWS Calorifiers | P | -42 | 6
F
A
Leak detection panel | P | -28 | 4
F
A
Lighting control modules | P | -28 | 4
F
A
Linear slot diffusers | P | -42 | 6
F
A
MCC panel | P | -42 | 6
F
A
Motorised dampers | P | -42 | 6
F
A
Motorised valve sets | P | -35 | 5
F
A
Outlet face plates | P | -28 | 4
F
A
Packaged generator set | P | -84 | 12
F
A
Pre-fabricated pipework | P | -28 | 4
F
A
Presence detectors / PIR’s | P | -28 | 4
F
A
Presurisation unit | P | -28 | 4
F
A
Pump set | P | -42 | 6
F
A
Specialist light fittings | P | -84 | 12
F
A
Standard open plan light fittings | P | -42 | 6
F
A
Static transfer switch | P | -70 | 10
F
A
Tap off units | P | -56 | 8
F
A
UPS batteries | P | -42 | 6
F
A
UPS unit | P | -70 | 10
F
A
Utility connections | P | -84 | 12
F
A
Underfloor heating | P | -28 | 4
F
A
Formulas:
Order By = [Expected Delivery to Site]-([Lead In Period (Weeks)]*7)